## Slide 1
August 2026
Adult Social Care Improvement Plan 2026/2028
Enabling Gloriously Ordinary Lives

## Slide 2
Contents
1. Executive Summary and Improvement Plan on a Page | Page 3
2. Introduction | Page 6
3. Designing the ASC Target Operating Model: Overview | Page 15
4. Responding to CQC Priorities | Page 22
5. ASC Improvement Programme Structure | Page 31
6. Delivering the ASC Improvement Programme | Page 66
Appendix | 
1. Progress to date | Page 80

## Slide 3
1. Executive Summary and Improvement Plan on a Page

## Slide 4
The Improvement Plan brings together in one place the changes and transformation required in Adult Social Care at Nottingham City Council to deliver an improved delivery model and outcomes for local people. Specifically, this plan includes:
Development and delivery of the Adult Social Care ‘Enabling Gloriously Ordinary Lives’ strategy
Continued improvements required in response to MHCLG oversight
Improvements required in response to the CQC assessment and assurance process, including DHSC oversight
Other local priorities identified or underway to deliver improvement
To deliver it successfully:
Teams in the department will need to work collaboratively together
Access the support and expertise of other corporate functions and colleagues
Work closely with partners and the care market
Most importantly, include people and communities
Leadership, governance, accountability and effective performance management are givens.
Together the programmes are creating a new Target Operating Model for Adult Social Care in Nottingham City.
Executive Summary
This plan is an overarching and aligned transformation plan structured into 3 workstreams with 15 delivery programmes. It is a 2-year plan, recognising the timeline for local government reorganisation. Much of the work is front-loaded whilst recognising that sustainable change and an improvement culture take time to bed in.

## Slide 5
Improvement Plan on a Page: Delivering a TOM for ASC
WS0: Enabling Gloriously Ordinary Lives Strategy
Financial stewardship
Quality
Regulatory compliance
Adult Social Care Target Operating Model
Strategic aims
Strategic workstreams
Collaborative Delivery
WS1: Improving outcomes for people
WS3:
Critical enablers for success
WS2: Building delivery capability
2.1 Strategic Commissioning Development Programme
2.2 Building a Service Development
Function
2.3 ASC Development Programme: Structures and workforce
3.1 Co-production with people
3.2 Equality Diversity and Inclusion
3.3 Leadership, Governance & Financial Stewardship
3.4 Data, performance and analytics
3.5 Digital
1.4 Enabling a system that works
1.5 Practice Improvement & Workforce development
1.6 ASC Operational Services Redesign
1.1 Living Well Earlier
1.2 Living Well at Home
1.3 Living Well with Complex Care Needs
Commissioning & Partnerships
Adult Social Care Operations
Service Development
Corporate Enablers
Partners
Care Providers
Coproduction with people & communities

## Slide 6
2. Introduction

## Slide 7
This Improvement Plan sets out how Nottingham City Council will strengthen Adult Social Care through delivery of a single, coherent improvement plan that describes:
our shared ambition, grounded in the Enabling Gloriously Ordinary Lives strategy
the 15 key programmes of work that will make that ambition real in practice, across 3 workstreams
how we will act together as one system, alongside communities and partners
how we will involve people in driving forward improvement
the benefits and outcomes to be delivered
the resources required to deliver change
the key risks, issues and interdependencies that must be actively managed
This plan is a statement of how we intend to exercise our responsibilities as a local authority, and how we will ensure that improvement is experienced by people who draw on care and support, not just measured by the organisation. These challenges are connected.
They affect how people experience care and support, how staff are able to practice, how well we use resources and how effectively we work as a system. Our improvement plan is about changing those conditions, not simply responding to the consequences.
This is a single plan for the directorate to cover ongoing assurance and accountability for improvement linked to MHCLG oversight, CQC assessment outcomes including DHSC oversight and demonstrating Care Act compliance. It is a 2 year plan, recognising upcoming local government reorganisation by 2028.
Introduction: purpose and scope of the improvement plan

## Slide 8
Strong leadership and governance
Data-led decision making and demand insight
Workforce capability and culture change
Co-production embedded in design and delivery
Clear performance measures linked to outcomes
1. More people living independently at home for longer, feeling listened to & respected and having control over their life
2. Reduced demand at the “front door” and in crisis services
3. Faster, more consistent and equitable access to the right support
4. Stronger communities and informal support networks
5. A confident workforce able to work differently
6. A financially sustainable adult social care system
1. Start with life, not services
2. Intervene earlier prevent escalation
3. Build community and connection
4. Enable a sustainable, responsive system
5. Work as one system
6. Measure what matters and continuously improve
Moving from a model that:
1. Responds late to crisis
2. Manages demand through eligibility and control
3. Focuses on services rather than people
To a model that:
1. Intervenes earlier and prevents escalation
2. Starts with people’s lives, not services
3. Builds on strengths, relationships and communities
4. Supports people to live well for longer
Our ambition for the future: Enabling Gloriously Ordinary Lives (strategy on a page)
Enable people in Nottingham to live gloriously ordinary lives in the place they call home, with the people and things they love, doing what matters to them.
Adult social care in Nottingham exists to:
1. Support independence, dignity and connection
2. Sustain caring relationships and communities
3. Prevent avoidable loss of independence and wellbeing
4. Act as a responsible steward of public resources
Our Purpose
Our Shift in Approach
Our Strategic Priorities
What Success Looks Like
Our Delivery Enablers

## Slide 9
A deliberate shift to enabling people to live well and safely on their own terms
Where we are now We are taking a clear and honest view of the challenges we face. These are not isolated issues and they reflect how the system has evolved over time. However, Nottingham is choosing to act. We all want to live in a place we call home, with the people and things we love, doing what matters to us. We are committed to addressing our challenges directly, with a consistent focus on enabling people to live gloriously ordinary lives.
What we are Changing…
Adult social care works best when it starts with life, not services and when it is shaped around what matters to people, carers and residents.
We are moving from a system that responds to pressure, to one that is designed around people’s lives, with:
stronger grip
earlier intervention
shared accountability across the system
We are changing the conditions in which Nottingham delivers adult social care, not simply improving performance within the same model. This is a deliberate shift away from managing people through systems, and towards enabling people, carers, and workforce, communities to live well safely and on their own terms.

## Slide 10
Our commitment to improvement: Our local people and communities
What we Recognise Needs to Improve
People too often experience Adult Social Care as fragmented, slow, unresponsive and difficult to navigate.
Delays, unclear ownership and multiple hand-offs mean support is too often linked to crisis rather than earlier help.
People’s experience is shaped not only by practice, but by the structures, pathways and performance arrangements behind the scenes.
We have not yet delivered a consistently humane, joined-up experience across the whole system.
What we are Committed to Changing…
We will design support around ordinary lives, not around services or organisational boundaries.
We will strengthen earlier intervention and prevention so people can get support sooner and on their terms.
We will improve first conversations, continuity and ownership through more relational ways of working.
We will build more neighbourhood-based, community-connected responses, including early help, community support, technology and personalised support.
We will support choice and personalisation enabling people to feel in control, respected and listened to whilst staying safe
We will recognise and support unpaid carers as partners in care, not as an afterthought.

## Slide 11
What we Recognise Needs to Improve
Staff do not consistently have the time, tools or conditions needed to practice in relational, strengths-based practice ways
Systems, processes, structures do not always enable good professional judgement or consistent practice
Practice is not yet consistent and equitable enough across the city and has not kept pace with the model of care we want to deliver
Staff are not always able to come together in ways that support locality-based working, learning and shared accountability.
We need to strengthen development, confidence and capability, including how technology is used in everyday practice
What we are Committed to Changing…
We will support staff to work in more locally-based, neighbourhood-connected ways
We will reduce avoidable hand-offs and strengthen ownership, accountability and continuity through a case worker approach
We will establish a more consistent and equitable practice model across the city, grounded in relational, strengths-based practice
We will invest in professional development, supervision and capability so staff can practise confidently, ethically and in a personalised way
We will make technology a practical, everyday part of how people work productively and personalise support
Our commitment to improvement: Our workforce

## Slide 12
Our commitment to improvement: Our financial stewardship
What we Recognise Needs to Improve
Demand has grown faster than our ability to respond sustainably
We have relied too heavily on short-term measures to manage financial pressure, rather than consistently redesigning demand and pathways
We do not yet have a strong enough line of sight between demand, spend, quality and outcomes
Financial management has too often been driven by immediate pressure rather than long-term system redesign and best value
What we are Committed to Changing…
Strengthen financial stewardship through linking demand, activity, cost and outcomes
Strengthen budget manager accountability, ensuring cost drivers are understood and actively managed
Support earlier, preventative approaches to reduce avoidable escalation and long-term pressure – enabling independence and preventing harm
Seek to align resources to support that makes the greatest difference to people’s wellbeing and outcomes
Move from short-term fixes to more sustainable financial planning, through service redesign, market shaping and better use of data
Measure what matters – defining success by better lives, not just activity or cost

## Slide 13
Our commitment to improvement: Our local partnerships
What we Recognise Needs to Improve
People do not consistently experience the wider system as joined-up around their lives
We have experienced fragmentation between Adult Social Care, health, housing, communities and the wider partnership landscape
Partnerships have not always delivered shared ownership of outcomes, risks and delivery
Relationships with parts of the care market have become strained, and trust needs to be rebuilt
This has contributed to duplication, delays and inconsistent experiences for local people
What we are Committed to Changing…
We will strengthen integration across the Council, with partners and communities: NHS, health, VCSFE, housing and academia with the aim of working as one system around people, not organisations
We will invest in our relationships with the care market: co-producing to deliver good outcomes, productively and efficiently
We will develop stronger shared ownership of outcomes with partners
We will invest in a city-wide approach to supporting care professionals, attracting and retaining talent
We will strengthen place-based working across neighbourhoods and communities
We will align pathways to improve flow, reduce duplication and support earlier intervention

## Slide 14
Our 2-year strategy: features of how the future ASC system will operate for people
Life led, not service led
Starting with what matters to people who draw on care and support, their carers and families, recognising them as experts in their own lives. Support is shaped around people’s priorities and aspirations, rather than organisational convenience or predefined pathways
Closer to home and neighbourhood based
Organising support around where life happens, strengthening connection to place, community and relationships. Neighbourhoods are treated not just as delivery units, but as sources of resilience, belonging and support.
Preventative by default
Acting earlier and relationally to support independence, wellbeing and connection, reducing escalation, distress and avoidable dependency. Prevention here means doing the right things sooner—not withdrawing responsibility or support.
Co‑produced as standard
Sharing power with people who draw on care and support, carers, residents and the workforce. Decisions are made with people, not for them, and lived experience actively shapes how services develop and improve.
Equity driven
Recognising that not everyone starts from the same place and that inequality shapes experience and outcomes. Effort, investment and attention are targeted where disadvantage and inequality have the greatest impact on people’s lives.
Relational, safe and humane
Valuing relationships, continuity and trust as essential conditions for good outcomes. Safeguarding and stewardship are exercised ethically, transparently and proportionately, with dignity and humanity at their core.
Financially responsible and sustainable
Using public money wisely to improve lives and reduce long‑term pressure, recognising that sustainability is achieved through good design, early support and humane practice - not short‑term cost control that shifts risk elsewhere.

## Slide 15
3. Designing the Adult Social Care Target Operating Model: overview

## Slide 16
Vision
Outcomes
Objectives
Leadership & governance
Performance & analytics
Practice & processes
Workforce structure & capabilities
Technology and Data
Culture and behaviours
Operating model and organisational design
Strategy
Relationship between the TOM and Improvement Plan
The Target Operating Model is a blueprint for how a directorate functions, indicating the key elements and how they work together.
For Nottingham City Council the scope of the Target Operating Model is Adult Social Care operational teams, the Commissioning and Partnerships team and the Service Development team.
Whilst respecting their different areas of responsibility, only by working and operating together, co-ordinating and supporting each others activity, will the required improvement be delivered. Enablers are common.
The Improvement Plan is the delivery programme through which changes to the target operating model and associated improvements will be delivered in order to deliver the ASC strategy “Gloriously Ordinary Lives”, CQC assessment improvement actions, regulatory compliance, and other priority areas for action.

## Slide 17
These design principles will be used to steer internal redesign and change activities. They have been derived from the strategy, but reflect internal change required to delivery the strategic principles in Enabling Gloriously Ordinary Lives. They will act as a common thread across the TOM to help ensure efforts and projects are aligned.
People at the Centre
Joined up, co-produced & co-ordinated
Be Care Act Compliant
& Meet Statutory Requirements
Provide Best Value
Clear & Simple By Design
Celebrate Continuous Improvement
Digital & Data Enabled
We use data and insight to design our service pathways and apply measurable indicators to track the progress and impact of any interventions. Digital supports better decision-making, streamline processes, and improves outcomes: improving equity, transparency, dignity and safety.
We deliver maximum value by balancing cost-effectiveness with quality, prioritising sustainability and long-term impact. Clear performance measures will track progress, ensuring accountability and continuous improvement. Success will be defined by better lives, not just activity and cost.
We design services and communications that are easy to understand and use, reducing effort for staff and residents.
We prioritise what makes the biggest difference to people’s lives and use resources accordingly. We embed a mindset to reflect, adapt and enhance. We support ongoing learning, experimenting and refinement with frequent evaluation, learning from lived experience, practice and data.
Our services, processes, decisions and training align with the Care Act 2014 and other relevant legislation. Digital literacy is embedded in practice, to enable evidence-based decision making.
We work as one system, joining up services, teams and partners around the person. Integration is designed to strengthen relationships, reduce hand‑offs and ensure people experience support as joined‑up, humane and responsive.
We start with what matters to people in their lives, relationships and communities. Support is personalised around people’s priorities and ordinary lives, enabling independence, wellbeing and dignity.
Target Operating Model Design Principles

## Slide 18
Enabling Gloriously Ordinary Lives Strategy
Preventative
Life-led
Strengths-based
NCC ASC Target Operating Model: High-level overview
Strategic ambition
End-to-end Persons pathway
Early help & front door
Assessment
Care & support planning
TEC + community offer + care
Review & outcomes
Cross- cutting functions
Strategic Commissioning
Brokerage & placements
Partnerships
Service development & quality assurance
Current pain points
Fragmented processes & hand-offs, variable information capture, duplication, inconsistent triage, unpredictable demand, communication, limited prevention / early intervention, capacity, waits, approach to risk, people placed in most intensive setting
Future pathway ambition
Prevention in the community
Streamlined and accessible information
Single front door
Effective triage
Digital pathways & self-service
Full grip: single owner, reduced hand-offs, local teams in neighbourhoods
Relational strengths-based: What Matters Most?
Outcomes focussed
Timely to reduce escalation
Life-led not service led
Least restrictive approach
Information gathered once, early
Personalisation & DPs
Automation and use of digital solutions for efficiency
Strong community offer before / blended with eligible care
Technology is promoted throughout
Care is close to home, appropriate, least intensive
Responsive services
Timely review enabled by data
Feedback on services driving quality & practice
Risk-based approach to review
Workforce structures, OD and capability
Strengths-based relational practice & meaningful outcomes
Data, analytics, performance and governance
Technology enabled care
Critical enablers

## Slide 19
The Improvement plan will impact:
People
Change structures to enable delivery of the strategy and increase capacity and capability
Co-production and EDI will be embedded
Embed an improvement culture
Processes and Practice
Reframe practice to be strengths-based, relational and focused on prevention
Redesign processes to be more frictionless for people and staff
Systems and Digital
Ensure that IT systems and digital support tools support efficient processes and practice model
Collaboration
Cement a programmatic and collaborative approach to how priorities are delivered, teams and services work together within the directorate, with other corporate colleagues, and with external partners and stakeholders
Impact and Scope of the Improvement Plan and Target Operating Model

## Slide 20
Impact and Scope of the Improvement Plan and Target Operating Model
Enabling Gloriously Ordinary Lives Strategy
Preventative
Life-led
Strengths-based
Adult Social Care Operations
Front door and community prevention
Assessment & short-term support / reablement
Technology enabled care
Long term care & support
Commissioning & Partnerships
Strategic needs assessment & forecasting
Market shaping and development
Strategic programme delivery
Performance monitoring and contract mgmt.
Brokerage & placements
Service Development
Driving workforce development
Improving and embedding strengths-based relational practice
Improvement and transformation in ASC operations
Public Health
Health promotion
Health prevention
Health inequalities
Health protection
Population health and needs assessment
Scope of Change Impacts to deliver Target Operating Model

## Slide 21
Commissioning Cycle
Design
Deliver
Evaluate
Manage
Analyse population data, needs, policy and insight​
Design services with people, staff, providers, partners and stakeholders​
Shape the market for long term delivery of requirements at best value​
Plan demand and capacity ​
Build strategic programmes to deliver long term ASC strategy​
Review service provision​
Evaluate impact: quality, outcomes, best value​
Analyse gaps​ & Identify areas for improvement​
Plan forward strategy and priorities​
Refresh commissioning intentions and pipeline
Decision-making: business case and options appraisal​
Specify requirements, KPIs and outcomes​
Baseline impact and outcomes framework​
Confirm commercial and pricing strategy ​
Procure / purchase services​
Mobilise services & contracts​
Decommission services​
Manage contracts / frameworks: performance, quality, compliance, delivery​
Maintain provider relationships ​
Manage market risk & sustainability​
Improve quality​
Deliver best value​
Access to services: manage day-to-day placements ​
Seek feedback and track outcomes​
Collaboration & Partnerships
Evidence, Data & Analytics
Communication
Co-production
Matrix Working

## Slide 22
4. Responding to CQC Priorities

## Slide 23
Nottingham City Council has been assessed by the CQC as part of their national programme. NCC was a pilot CQC assessment site in 2023 and was revisited in December 2025. The CQC assessment focuses on how local authorities meet their duties under Part 1 of the Care Act (2014) under 4 themes:
  How local authorities work with people
  How local authorities provide support
  How local authorities ensure safety within the system
  Leadership
The outcome of this assessment for Nottingham City Council was Requires Improvement, with significantly weak scores relating to two key areas:
  Safe pathways, systems and transitions
  Governance, management and sustainability
NCC is under additional scrutiny relating to these two areas by the Department of Health and Social Care (DHSC). The CQC has issued a formal Section 50 notification to the Department of Health and Social Care.
Overview of CQC assessment

## Slide 24
CQC strengths and remedial improvement activity underway
Whilst the overall outcome of the assessment was Requires Improvement there were areas of strength and good practice noted including:
  Committed and motivated workforce delivering person-centred care
  Strong examples of strengths-based practice and respecting people’s choices
  Prevention and early intervention delivering measurable impact
  Prevention Officers helping reduce demand for formal care
  Effective reablement and hospital discharge coordination
  Positive feedback from carers and strong Carers Hub offer
  Robust safeguarding arrangements with strong partnership working
  Effective multi-agency initiatives (e.g. Changing Futures)
Since the inspection visit took place in December 2025, a number of areas highlighted as concerns have already been progressed. This includes:
  Development of an ASC strategy, Enabling Gloriously Ordinary Lives
  Development of an ASC Improvement Plan
  Leadership team building stability and embedding improvement programme into systems and governance
Strengthening grip on backlogs, improving visibility of risk, and beginning work to simplify pathways
  Strengthening quality assurance and learning
  Improving market capacity and partnerships
  Developing data-driven performance management

## Slide 25
ASC Directorate Leadership Team recognise the significance of the issues raised in the CQC report. Many of the issues highlighted align with improvement activities already underway. Where this is not the case, consideration has been given to initiating new work or adapting business as usual priorities to deliver improvement; taking account of priorities, sequencing, interdependencies, resources and capacity across the entire improvement agenda programme.
To de-risk delivery and maximise success the CQC improvement actions have been analysed and mapped against the existing improvement plan (see next slide) to ensure alignment and enable a single improvement approach:
  One Improvement Plan
  One programme structure
  One governance and assurance mechanism
  An aligned set of priorities and delivery programmes
  Streamlined resources
  One narrative for staff, citizens, stakeholders and partners
Quality Statements | Assessing needs | Supporting people to live healthier lives | Equity in experience and outcomes | Care provision, integration and continuity | Partnerships and communities | Safe systems, pathways and transitions | Safeguarding | Governance, management and sustainability | Learning, improvement and innovation
Overall % QS score | 44% | 50% | 44% | 50% | 50% | 38% | 57% | 38% | 50%
Overall numerical score | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 1 | 2
Approach to Driving Improvement

## Slide 26
CQC Improvement area | Summary of Issues | Priority remedial actions | Improvement Plan Workstream | Senior Responsible Owners
CQC1: ASC Front Door | Lack of accessible information on the website and long wait times on the telephone (9+minutes) leads to a lack of confidence in the council's offer | Redesign of ASC first points of contact as part of TOM development | WS 1.6 ASC Operational services redesign | Director Service Development
 |  | Front door redesign project | WS 2.3 ASC Development Programme: Structures and Workforce | 
 |  | Technology Enabled Care Demonstrator | WS 3.5 Digital | Director Commissioning
CQC2: Assessments | Capacity & flow with significant waits for both initial care act assessments and reviews. Both hospital discharge and community assessments are affected by workforce limitations and bottle necks | Assessment redesign around people and practice Audit & recommendations to optimise Case management system (Liquid Logic) | WS 1.6 ASC Operational services redesign | Director Service Development
CQC Issues Requiring Improvement: Summary Findings (1)
As part of the analysis, the CQC findings were reviewed and grouped thematically to identify the common ASC areas requiring improvement.
The tables which follow map these CQC Assessment areas to the Improvement Plan Workstreams and their respective SROs. Priority remedial actions are in place, and some of the work is already underway.
Each CQC Improvement Area has been numbered to ensure activity delivered through the broader Improvement Plan Programme can be meaningfully reported on to assure regulators on progress directly linked to the CQC findings.

## Slide 27
CQC Improvement area | Summary of Issues | Priority remedial actions | Improvement Plan Workstream and Programme | Senior Responsible Owners
CQC3: Carers | Carer support gaps - both in identifying unpaid carers' needs in a timely way and in having sufficient respite services to meet demand once needs are known | Co-produce proactive, accessible carer support and flexible respite through VCSE and digital solutions | WS 1.1 Living well earlier | Director Commissioning
CQC4: Commissioning Development & Market sustainability | There are market capacity gaps, especially for LD, mental health, sensory, respite, supported living and PA provision, which can lead to out-of-area placements. Providers are experiencing sustainability pressures from fees, costs and delayed uplifts and there is weakened provider confidence and trust due to inconsistent communication. Need stronger provider engagement, contract monitoring and impact evaluation. A greater focus on working with the market to shape it to meet the needs of the population to ensure gaps do not emerge. For example, waits for advocacy services are at least 2-4 weeks, but can be months and a broader view of the market is needed to manage this. | Create case for investment in new structure Design and deliver a refreshed structure and workforce model that enables a shift to sustainable strategic commissioning within NCC Develop underpinning OD programme and commissioning toolkit Engage with partners and providers to build understanding and support for changes | WS 2.1 Strategic Commissioning Development Programme | Director Commissioning
CQC Issues Requiring Improvement: Summary Findings (2)

## Slide 28
CQC Issues Requiring Improvement: Summary Findings (3)
CQC Improvement area | Summary of Issues | Priority remedial actions | Improvement Plan Workstream and Programme | Senior Responsible Owners
CQC5: Co-production | Despite council efforts to understand their population through community engagement activity, citizen feedback opportunities on internal services, and good intentions, Co-production is not yet embedded routinely in the way the council works. There are weak feedback loops into strategy and decision-making and budget, resource and capacity constraints limit impact | Embed co-production throughout ASC operations and commissioning Develop a case for investment in co-production resources Develop a policy for remunerating co-production Test co-production approach through the TEC Demonstrator | WS 3.1 Co-production with people | Director Co-production
CQC6: CYP to Adult transitions | Weak transitions from children to adults' services. Transitions arrangements did not always ensure young people had a seamless transition to adult services of their care and support. | Establish a co-produced transitions pilot | WS 1.3 Living Well with Complex Care Needs | Director Commissioning
CQC7: Direct Payments | Decline in the uptake of Direct Payments and there is no routine, system-wide mechanism for DP review and payment. A clear process would help build staff confidence to help residents' set up their support with a Direct Payment attached. | Data and discovery: analyse demand, cost, and lived experience insight Expand Direct Payments to increase choice and control Develop governance and processes for accessing Direct Payments | WS 1.2 Living Well Earlier | Director Commissioning

## Slide 29
CQC Issues Requiring Improvement: Summary Findings (4)
CQC Improvement area | Summary of Issues | Priority remedial actions | Improvement Plan Workstream and Programme | Senior Responsible Owners
CQC8: Equality Diversity Inclusion & Access | Accessibility barriers for non-English speakers, people with sensory needs and digitally excluded people with delays and over-reliance on families for interpretation, BSL and advocacy. Published materials and web pages offer limited translated and easy read information, pushing residents to telephone lines - where the average call wait time is over 9 minutes. Specific gaps in culturally appropriate care provision for Black African and Caribbean, Muslim and LGBTQ+ residents, and current services lack sufficient capacity to guarantee cultural needs can be met. Incomplete equality data and intersectionality understanding limits opportunities to address health inequalities. | Discovery and research to baseline starting point across Commissioning, operations, practice and workforce | WS 3.2 Equality Diversity & Inclusion | Corporate Director for ASC & Health
 |  | Embed EDI into redesign of ASC first points of contact through co-production with citizens and people who draw on care and support | WS 1.6 Operational Service Redesign | Director Service Development
CQC9: Intermediate Care | Waiting lists to access reablement from the community, with mental health reablement waits at 8-12 weeks. An external Reablement provider refined their eligibility criteria, thus limiting the number and acuity of referrals they accept, increasing pressure on in-house provision so Hospital Discharges are prioritised. Structural capacity issues to be addressed through commissioning to stimulate the market, as well as operational, process and practice improvements | Review current home care, reablement, and discharge pathways Develop commissioning options and model redesign Engage providers and align system partners to build a joined-up neighbourhood model | WS 1.2 Living Well at Home | Director Commissioning

## Slide 30
CQC Issues Requiring Improvement: Summary Findings (5)
CQC Improvement area | Summary of Issues | Priority remedial actions | Improvement Plan Workstream and Programme | Senior Responsible Owners
CQC10: Leadership | Leadership instability has impacted strategic and operational work and that systems are required to ensure continuity should further changes occur. Council staff have experienced poor communication of key decisions, policy, and operational changes which have not been delivered in timely, consistent, or sensitive ways. | Design of first line management development programme linked to refreshed structures​ Review, refresh and communicate departmental governance with clarity of linkage to corporate governance and to assurance and oversight regime​ Co-production embedded into governance with people receiving care and support represented on all key decision-making groups | WS 3.3 Leadership, Governance and Financial Stewardship | Corporate Director for ASC & Health
CQC11: Mental Health & S&MD | Mental health review recommendations concerning section 117 processes being distinct from Care Act assessments and clear documentation and protocols to embed joint working with NHS partners have not been progressed. The prevailing lack of clarity is leading to avoidable discharge delays and a lack of accurate needs assessments. Limited accommodation offers for some people who experience severe and multiple disadvantage creates additional work pressures on the team who need to be resourceful when finding suitable placements | Review how current systems hinder good practice and joint working Build joint protocols which clarify and simplify processes | WS 1.5 Practice Improvement and Workforce development | Director Service Development
 |  | Review accommodation options for people experiencing severe and multiple disadvantage | WS 1.3 Living Well with Complex Care Needs | Director Commissioning

## Slide 31
CQC Issues Requiring Improvement: Summary Findings (6)
CQC Improvement area | Summary of Issues | Priority remedial actions | Improvement Plan Workstream and Programme | Senior Responsible Owners
CQC12: Partnerships | There are examples of meaningful partnership at both strategic and operational level with internal and external teams, however these are sometimes reliant on individual relationships rather than intentionally designed systems. Operationally, partners are not always consistently involved in reviews, care planning, and decision making. Strategically there are gaps around governance, accountability, and information-sharing arrangements. These gaps and inconsistencies translate into less timely interventions and confusion for partners and people accessing support; as well as organisations working antagonistically rather than collaboratively, which compound into worsening outcomes for people. | Develop a data-led Prevention Framework aligned to neighbourhood health, targeting need and integrating system partners Develop a VCFSE partnership and neighbourhood model | WS 1.2 Living Well Earlier | Director Commissioning
 |  | Commissioning & Partnerships to deliver market analysis and position statement Progress brokerage redesign with providers | WS 1.4 Enabling a System that Works | 
 |  | Strengthen local digital and innovation partnerships | WS 3.5 Digital | 
CQC13: Performance | The council is not yet using data in ways that triangulates and builds information into actionable insights which can inform commissioning, practice, and governance. There is a particular gap round outcomes for people. The ambition is to become an evidence-driven local authority but there is a resource gap which needs to be addressed. | Establish Performance & Quality Board Joint approach with corporate A&I teams Analysis of demand, flow and pressure points with priorities for deeper modelling Reporting & architecture approach – dashboards, self-service, automated reporting | WS 3.4 Data Performance & Analytics | Corporate Director for ASC & Health

## Slide 32
CQC Issues Requiring Improvement: Summary Findings (7)
CQC Improvement area | Summary of Issues | Priority remedial actions | Improvement Plan Workstream and Programme | Senior Responsible Owners
CQC14: Practice Improvement | Inconsistent practice and processes across adult social care has led to issues such as unmitigated risks, unplanned and disorganised care, and delayed interventions, which result in people feeling less safe and partner organisations uncertain about accountability for managing individuals' care. Processes around assessments, reviews, funding panels and “waiting well” are unclear or not embedded. Variable communication and planning when working with partners and inconsistent safeguarding thresholds and DoLS oversight. Learning not prioritised with gaps in staff training, supervision, confidence and specialist input. Need for stronger practice standards, clearer accountability, better workforce support, and more consistent use of learning, feedback and quality assurance to improve outcomes. | Baseline current Quality Assurance (QA), practice development and performance approaches across ASC​ Identify duplication, gaps and inconsistency in QA and workforce development​ Define core principles for practice, QA and continuous improvement (Strategy-aligned)​ Develop and test initial QA and practice framework options​ Map links to performance, workforce and commissioning to ensure alignment​ Identify key enablers (data, leadership, OD, governance)​ Review how current systems and processes support (or hinder) good practice across pathways​ Identify opportunities to simplify workflows, reduce duplication and improve recording quality​ Define priority system/process changes required to support the practice framework (aligned to BetterGov discovery) | WS 1.5 Practice Improvement & Workforce Development | Director Service Development

## Slide 33
CQC Issues Requiring Improvement: Summary Findings
CQC Improvement area | Summary of Issues | Priority remedial actions | Improvement Plan Workstream and Programme | Senior Responsible Owners
CQC15: Transfers of Care | Weak oversight of out-of-area transfers, long waits for annual reviews, unclear accountability for safe handovers, and gaps in hospital discharge system integration — i.e. absence of CHC input in the discharge hub. Risks around continuity, timely decision-making, and ensuring people move safely between services or areas. | Review current home care, reablement and discharge pathways | WS1.2 Living Well at Home | Director Commissioning
 |  | Design progression pathways and step-down models | WS 1.3 Living Well with Complex Care Needs | 
CQC16: Waiting times | Residents are experiencing avoidable waits for a number of ASC assessments, transfers, and equipment which negatively impact on their quality of life. Bottlenecks are caused by capacity issues, unnecessarily complex processes and pathways, and a lack of oversight. | End to end pathway review from the lens of the person drawing on care and support Assessment redesign | WS 1.6 Operational Services Redesign | Director Service Development
 |  | TOM development | WS 2.3 ASC Development Programme: Structures & Workforce | 
CQC17: VCFSE | The council's relationships with its VCFSE is described as one-way with limited investment/support for grassroots groups with relationships compromised due to poor communication linked to staff turnover and commissioning decisions. Council staff not always aware of VCSE services, but strategic engagement is improving but not yet embedded. There are some gaps in preventative services, e.g. employment support | Co-produce community-based pathways and VCFSE network model | WS 1.1 Living Well Earlier | Director Commissioning
 |  | Develop a first phase Co-production plan in collaboration with VCFSE | WS 3.1 Co-production with people | Director Co-Production

## Slide 34
5. Adult Social Care Improvement Programme Structure

## Slide 35
Improvement Plan on a Page: Delivering a Target Operating Model for ASC
Enabling Gloriously Ordinary Lives Strategy
Financial stewardship
Quality
Regulatory compliance
Adult Social Care Target Operating Model
Strategic aims
Strategic workstreams
Collaborative Delivery
WS1: Improving outcomes for people
WS3:
Critical enablers for success
WS2: Building delivery capability
2.1 Strategic Commissioning Development Programme
2.2 Building a Service Development
Function
2.3 ASC Development Programme: Structures and workforce
3.1 Co-production with people
3.2 Equality Diversity and Inclusion
3.3 Leadership, Governance & Financial Stewardship
3.4 Data, performance and analytics
3.5 Digital
1.4 Enabling a system that works
1.5 Practice Improvement & Workforce development
1.6 ASC Operational Services Redesign
1.1 Living Well Earlier
1.2 Living Well at Home
1.3 Living Well with Complexity
Commissioning & Partnerships
Adult Social Care Operations
Service Development
Corporate Enablers
Partners
Care Providers
Coproduction with people & communities

## Slide 36
Purpose | Scope
To define and deliver the Enabling Gloriously Ordinary Lives strategy, setting a clear, shared direction for Adult Social Care that shifts practice, commissioning and system behaviour towards prevention, independence and person-centred outcomes. | Strategy development, refinement and approval Engagement and Co-production activity (staff, citizens, partners) Communications and narrative development Alignment to Operating Model and Commissioning delivery plans Outcomes, benefits and performance framework development Governance, assurance and reporting
Current phase: Key activities | Key Deliverables & Milestones
Consolidate insight from Strategy Task & Finish Group, engagement activity and timeline outputs Analyse feedback to identify priorities, themes and gaps Refine the strategy and get corporate sign off Align strategy to Operating Model and commissioning programmes: refine ASC Improvement plan delivery plans in line with strategy updates. Draft and refine communications and engagement approach for mobilising the strategy | Draft strategy communication and engagement (completed Jul 2026) Engagement report - Jul 26 Thematic synthesis session- insights and recommendation – Jul 26 Refinement of the strategy – Jul 26 Final strategy at ASC DLT, CLT, Improvement Board – Jul – Aug 26 Corporate Executive Sign off – Sep 26 Mobilisation – Autumn 26
Outcomes | CQC alignment
Clear, consistent vision embedded across ASC Improved citizen experience and outcomes (independence, wellbeing, choice) Stronger Co-production and system partnership working Alignment between strategy, delivery and commissioning decisions Improved ability to measure outcomes (not just activity) Cultural shift towards relational, strengths-based practice | 
ASC Strategy (1 of 2)
SROs: Strategic Director ASC & Director Co-production

## Slide 37
Delivery resources | Key risks and mitigations
SRO - Director Delivery Lead Strategy Task & Finish Group (comms, engagement, Co-production) Change Delivery (project management support) Communications and OD leads Heads of Service and operational leads VCSE, community and system partners | Engagement gaps (seldom-heard groups):→ Targeted outreach via VCSE and community networks Strategy not translating into delivery:→ Explicit alignment to TOM programmes and governance routes Capacity constraints:→ Prioritisation, T&F approach, escalation through governance Unclear or unmeasurable outcomes:→ Align early with Performance & Analytics programme Duplication / engagement fatigue:→ Single coordinated engagement and comms plan
Key stakeholders | Key Dependencies/ Interdependencies
ASC Staff and Heads of Service Citizens, carers and people drawing on care and support VCSE organisations and community partners Health partners and wider system Communications, OD and workforce leads Senior leadership and governance forums (DLT / Improvement Board) | Performance & Analytics: Outcomes framework and reporting capability Structures & Workforce: Embedding Strategy principles into operating model Service Development & QA: Defining “what good looks like” in practice Commissioning Programmes: Aligning investment and market shaping to Strategy outcomes
Future phases | 
Design Finalisation (Summer 2026):Finalise strategy, outcomes and governance; align to TOM and commissioning Mobilisation (Autumn 2026):Embed into delivery plans, launch comms, prioritise early actions Implementation (Autumn 2026–2027):Deliver through TOM and commissioning; track progress and refine delivery Embedding (2026–2027 ongoing):Build consistent practice, behaviours and culture across ASC Benefits & Improvement (2027 onwards):Measure outcomes, use insight to improve, refresh strategy | 
ASC Strategy (2 of 2)
SROs: Strategic Director ASC & Director Co-production

## Slide 38
Programme | Purpose | SRO
1.1 Living Well Earlier | Shift from reactive, service-led care to a preventative, life-led approach that strengthens community support and reduces reliance on formal services. | Director Commissioning
1.2 Living Well at Home | Enable people to live at home with the right support, at the right time, reducing escalation into formal care. | Director Commissioning
1.3 Living Well with Complex Care Needs | Deliver strengths-based, progression and recovery-focused support that improves outcomes and reduces reliance on high-cost care. | Director Commissioning
1.4 Enabling a System That Works | Stabilise, sustain and transform the market, enabling better outcomes through stronger commissioning, governance and partnerships. | Director Commissioning
1.5 Practice Improvement and Workforce Development | To ensure continuous improvement and consistent quality in Adult Social Care, so people receive better support through an embedded culture of learning and accountability, also ensuring that core systems, processes and tools are designed around practice that support high-quality care and decision-making. | Director Service Development
1.6 ASC Operational Services Redesign | Design and implement a refreshed end to end customer journey in ASC to promote early intervention and prevention, stream-lined efficient processes, improved flow, and better outcomes for people. | Director Service Development
Workstream 1 overview: Improving Outcomes for People

## Slide 39
Purpose | Scope | 
Shift from reactive, service-led care to a preventative, life-led approach that strengthens community support and reduces reliance on formal services. | Transform day services into flexible, preventative pathways that build independence Expand Direct Payments to increase choice and control, underpinned by strong governance Deliver proactive, co-produced carer support and flexible respite through VCSE and digital solutions Redesign the Information & Advice front door to enable early triage, digital access, and community navigation Strengthen partnership working and commissioning through shared data and system collaboration Build neighbourhood-based, asset-driven support to improve access to prevention and reduce demand | 
Current phase: Key activities | Deliverables and Milestones | 
Data & discovery: analyse demand, cost, and lived experience insight Develop a data-led Prevention Framework aligned to neighbourhood health, targeting need and integrating system partners Define commissioning intentions and business cases for preventative pathways Co-produce community-based pathways and VCSE network model Mobilise early help pathways and delivery plans and identify opportunities for alignment to Neighbourhood Health plans | Prevention & Early Help commissioning framework – June 2027 VCSE partnership and neighbourhood model – August – December 2026 Digital Information & Advice front door and TEC-enabled approach – August – December 2026 Business cases and implementation plan – August 2026) | 
Outcomes | CQC alignment | 
Reduced reliance on statutory care and crisis intervention Increased use of community and preventative services Improved independence, wellbeing and progression into community life | Partnerships VCFSE Performance | Direct Payments Carers
1.1 Living Well Earlier (1 of 2)
SRO: Director Service Development

## Slide 40
Delivery resources | Key risks and mitigations
C&P commissioning team Change Delivery support (PM, BA, WoW Coach) Data and analytics support Finance support for developing business cases for investment £ - investment | VCSE capacity and visibility gaps → targeted market development + directory/TEC Reactive system behaviours persist → strong governance + commissioning levers Benefits not realised early → clear prevention metrics (e.g. contacts diverted, DP uptake)
Key stakeholders | Key interdependencies
VCSE / community organisations Public Health and NHS partners Citizens, carers and communities Communities, Environment and Resident Services Directorate ​ | Enabling a System that Works (market shaping, brokerage) Performance & Analytics (data, insight, measures) Structures & Workforce (neighbourhood working) Wider Neighbourhood health programme prevention strategies
Future phases | 
Scale prevention pathways and investment shift Embed long-term preventative commissioning model | 
1.1 Living Well Earlier (2 of 2)
SRO: Director Service Development

## Slide 41
Purpose | Scope
Enable people to live at home with the right support, at the right time, reducing escalation into formal care. | Redesign intermediate care pathways into a joined-up neighbourhood model Develop a new home care model focused on independence, flexibility and outcomes Deliver strategic accommodation planning and pathway alignment Embed technology, equipment and enablement as core offer
Current phase: Key activities | Deliverables and Milestones
Review current home care, reablement and discharge pathways Develop commissioning options and contract model redesign Deliver accommodation needs assessment (June 2026) Engage providers and align system partners | New home care and intermediate care model discovery phase report – September 2026 Accommodation strategy and pathway plan - August/September 2026 Commissioning and procurement approach – September 2027 TEC and enablement integration – December 2026 Key milestones: June 2026 → Sept 2027 delivery phases
Outcomes | CQC alignment
Reduced delays and improved flow from hospital to home Increased independence and reduced ongoing care demand Reduced admissions and reliance on residential care Clear accommodation pathways and improved market stability | Intermediate care Transfers of Care / Discharge
1.2 Living Well at Home (1 of 2)
SRO: Director Service Development

## Slide 42
Delivery resources | Key risks and mitigations
C&P commissioning team Change Delivery support (PM, BA, WoW Coach) Data and analytics support Finance support for developing business cases for investment £ - investment | Fragmented pathways persist → integrated neighbourhood model Provider market fragility → contract redesign + engagement Demand/capacity mismatch → improved data and modelling
Key stakeholders | Key interdependencies
Providers (home care, supported living, etc.) Brokerage and operational teams Housing and health partners | Living Well Earlier (prevention) Living Well with Complexity (specialist pathways) Enabling a System that Works (contracts, brokerage)
Future phases | 
Procurement and mobilisation Ongoing market development and quality improvement | 
1.2 Living Well at Home (2 of 2)
SRO: Director Service Development

## Slide 43
Purpose | Scope
Deliver strengths-based, progression and recovery-focused support that improves outcomes and reduces reliance on high-cost care. | Develop strategic accommodation and support models for complex needs Reduce out-of-area and residential placements Implement progression and recovery pathways and step-down models Improve transitions and co-produced support for young people Strengthen system commissioning with health and partners
Current phase: Key activities | Deliverables and Milestones
Analyse demand, pathways and high-cost placements Develop commissioning intentions (1, 3, 5 years) Design progression pathways and step-down models Establish co-produced transitions pilot | Complex needs commissioning strategy findings report – September 2026 Pathway redesign and progression model report – September 2026 Transitions pilot and service models project established – August 2026
Outcomes | CQC alignment
More people supported locally in least restrictive settings Reduction in high-cost and out-of-area placements Improved independence and better outcomes for people with complex needs | Transfers of Care / Discharge CYP to Adults transitions People living with severe and multiple disadvantage
1.3 Living Well with Complex Care Needs (1 of 2)
SRO: Director Service Development

## Slide 44
Delivery resources | Key risks and mitigations
C&P commissioning team Change Delivery support (PM, BA, WoW Coach) £ | Lack of suitable provision → targeted market development Crisis-led placements continue → earlier planning + pathway redesign System fragmentation → joint commissioning and governance
Key stakeholders | Key interdependencies
Health partners, housing, providers Adult operational teams CYP and transitions services Citizens and families | Living Well at Home (pathways) Enabling a System that Works (market shaping) TOM: Performance & Analytics (demand modelling)
Future phases | 
Delivery and scaling of redesigned pathways Long-term market reshaping | 
1.3 Living Well with Complex Care Needs (2 of 2)
SRO: Director Service Development

## Slide 45
Purpose | Scope
Stabilise, sustain and transform the market, enabling better outcomes through stronger commissioning, governance and partnerships. | Implement consistent pricing, contract and financial frameworks Strengthen QA, contract management and governance Develop market intelligence, demand and capacity insight Improve brokerage, provider engagement and system design
Current phase: Key activities | Deliverables and Milestones
Deliver market analysis and position statement Develop pricing model and contract frameworks Establish QA and governance approach Progress brokerage redesign and provider engagement | Market Analysis and Market Position Statement – September 2026 Pricing and contract model implementation – November 2026 QA and contract management framework – November 2026 Brokerage model and provider engagement framework – March 2027
Outcomes | CQC alignment
Reduced spot purchasing and improved value for money Improved risk visibility and quality assurance Better demand/capacity insight and decision-making Stronger provider relationships and market resilience | Shaping the market VCFSE sector Partnerships
1.4 Enabling a System that Works (1 of 2)
SRO: Director Commissioning

## Slide 46
Delivery resources | Key risks and mitigations
C&P commissioning team Change Delivery support (PM, BA, WoW Coach) Analysis & Insight (A&I) £ | Fragmented system and inconsistent practice → standardised frameworks Limited data and insight → shared intelligence and dashboards Provider market instability → structured engagement + incentives
Key stakeholders | Key interdependencies
Providers and market partners Brokerage, finance, operations Public Health, housing, system partners | All C&P programmes TOM: Performance & Analytics Corporate transformation (CSIP, finance, governance)
Future phases | 
Full implementation of operating model Continuous optimisation of market and commissioning system | 
1.4 Enabling a System that Works (2 of 2)
SRO: Director Commissioning

## Slide 47
Purpose | Scope | 
To ensure continuous improvement and consistent quality in Adult Social Care, so people receive better support through an embedded culture of learning and accountability. This includes ensuring that core systems, processes and tools are designed around practice, enabling staff to work effectively and record meaningful information that supports high-quality care and decision-making. | Practice standards, framework and pathways (what “good” looks like) Quality Assurance Framework (audit, review, challenge and learning loops) Workforce capability, development and Continuous Professional Development (skills, supervision, leadership) Performance management linked to quality and outcomes (not just activity) Continuous improvement approach (feedback → insight → improvement → embedding) Alignment to Strategy principles and outcomes across practice Practice-led system and process design (ensuring Liquidlogic / ContrOCC and wider tools are aligned to practice, reduce duplication and support good decision-making) | 
Current phase – Discovery & Definition: Key activities | Deliverables and Milestones | 
Baseline current Quality Assurance (QA), practice development and performance approaches across ASC Identify duplication, gaps and inconsistency in QA and workforce development Define core principles for practice, QA and continuous improvement (Strategy-aligned) Develop and test initial QA and practice framework options Map links to performance, workforce and commissioning to ensure alignment Identify key enablers (data, leadership, OD, governance) Review how current systems and processes support (or hinder) good practice across pathways Identify opportunities to simplify workflows, reduce duplication and improve recording quality Define priority system/process changes required to support the practice framework (aligned to BetterGov discovery) | Phase 1 Quality Assurance (QA) Policy agreed and published – July 2026 Practice Framework defined and signed off – July 2026 Practice Standards developed and ready for rollout – July 2026 QA Audit Tool designed and initial rollout complete – July 2026 Learning & Development (L&D) offer (phase 1) launched – “What Matters” assessment and new Support Plan agreed and implemented into practice approach – October 2026 | 
Outcomes | CQC alignment | 
Consistent, high-quality and relational practice across ASC Clear understanding of what “good” looks like and how it is measured Improved workforce capability, confidence and accountability Stronger link between performance, quality and outcomes Embedded culture of continuous learning and improvement Systems and processes that support relational practice, reduce administrative burden and improve the quality of information recorded | Assessments Practice Improvement Carers | Mental Health
1.5 Practice Improvement and Workforce Development (1 of 2)
SRO: Director Service Development

## Slide 48
Delivery resources | Key risks and mitigations
Core delivery team (QA, workforce development, OD, performance) Heads of Service and operational leads Support from HR, OD, Performance & Analytics and governance functions Programme management and improvement support £ – to be confirmed (training / OD / capacity requirements) | Limited workforce / OD / QA capacity→ Mitigation: Prioritise critical components, phased delivery, task & finish groups Lack of clarity on “what good looks like” across services→ Mitigation: Co-produce standards, align Practice Improvement and Workforce Development and Strategy principles Disconnect between performance and quality→ Mitigation: Align QA framework with metrics and Performance & Analytics programme Change fatigue / engagement risk→ Mitigation: Strong comms, Co-production, visible leadership and early wins Dependency on corporate support (HR, OD, data)→ Mitigation: Clear ownership, early escalation and aligned governance Systems and processes not aligned to practice → Mitigation: Prioritise practice-led system redesign and ensure clear ownership between programmes
Key stakeholders | Key interdependencies
ASC Heads of Service and operational teams Workforce / OD / HR leads Analysis & Insight Performance & Analytics Programme Communications and engagement lead(s) Partners (where workforce/practice alignment required) Citizens and people who draw on care (Co-production) | Performance & Analytics: defines metrics, reporting and insight ASC Development Programme: Structures and Workforce: defines roles, capacity and organisational model Practice Improvement and Workforce Development: defines practice standards, pathways and practice-led system requirements Commissioning programmes: align “good practice” with commissioned services Analysis & Insight: provides data architecture, governance and analytical capability Corporate governance / CSIP: assurance, reporting and accountability
Future phases – Phase 2 | 
Embedding & maturing (2026–27): Embed practice standards, Quality Assurance and supervision across ASC. Scale Quality Assurance audit and learning loops into business-as-usual. Establish Quality Assurance forums and clear escalation routes. Strengthen supervision and professional leadership. Improve data quality and performance insight with A&I. Use QA, complaints and lived experience to drive continuous improvement. Implementation of priority actions identified by BetterGov to improve case management system. | 
1.5 Practice Improvement and Workforce Development (2 of 2)
SRO: Director Service Development

## Slide 49
Purpose | Scope
Design and implement a refreshed end to end customer journey in ASC to promote early intervention and prevention, stream-lined efficient processes, improved flow, and better outcomes for people. | End to end pathway review from the lens of the person receiving care and support: pain points, flow, accountabilities (hand-offs, escalation) Front door redesign Assessment redesign Case Management System Optimisation Review and improvements in in-house provision
Current phase – Discovery & Definition: Key activities | Key Deliverables & Milestones
End to end pathway review from the lens of the person receiving care and support Establish front door redesign programme: targeted discovery Assessment redesign Audit and recommendations to enhance LAS | End to end pathway review (co-produced) – Jul / Aug 2026 Pathway redesign roadmap: priority activities and timeline - Sep 2026 Front door discovery – Jul / Aug 2026 Front door redesign – Sep / Oct 2026 Assessment redesign - May / Aug 2026 LAS optimisation – July to December 2026
Outcomes | CQC alignment
Improved flow and reduced delays across pathways; reduction in waiting times Improved experience: reduction in complaints; positive feedback Clear accountability and decision-making Workforce aligned to demand and prevention Consistent, person-centred practice Financially sustainable operating model | ASC Front door EDI & Access Waiting times Assessments
1.6 Operational Services Redesign (1 of 2)
SRO: Director Service Development

## Slide 50
Delivery resources | Key risks and mitigations
Delivery Team: Heads of Service: Support from other functions: BA support Data and analytics IT | Capacity constraints (HR / SMEs / operations)→ Prioritise critical path, use T&Fs, escalate early Weak data (demand / workforce assumptions)→ Iterative modelling, validate with operational insight, align with Performance and Analytics programme Cross-workstream misalignment→ Shared principles, governance alignment, integration checkpoints Affordability / financial envelope→ Scenario modelling, align with Finance, phased implementation Stakeholder engagement / consensus risk→ Structured workshops, clear ownership, governance escalation
Key stakeholders | Key Dependencies/ Interdependencies
Nottingham Health &Care Point Finance Business Partner: The Adults Social Care workforce People who draw on care and support VCFSE, Health Partners Wider NCC colleagues: Estates, DLTs | Strategic commissioning programmes: Living Well Earlier is key to align to front door ASC Development programme (structures and workforce): alignment between neighbourhood structures and end to end pathway Finance assumptions and affordability parameters Alignment with other Operating Model programmes and Commissioning: Performance & Analytics Programme: Delivery depends on timely access to accurate demand, activity and performance data, system discovery insights and aligned system capability. These underpin workforce modelling, role design, pathway optimisation and implementation feasibility Practice Improvement & Workforce Development: to define how practice works, what “good” looks like, and what capability the workforce must be designed to deliver
Future phases | 
Deliver forward prioritised programme of end to end pathway redesign In-house service provision: review and improvement programme Embedding & Improvement: track benefits, refine and stabilise model | 
1.6 Operational Services Redesign (2 of 2)
SRO: Director Service Development

## Slide 51
Programme | Purpose | SRO | Delivery Lead
2.1 Strategic Commissioning Development Programme | Design and deliver a refreshed structure and workforce model that enables a shift to sustainable strategic commissioning within NCC, to deliver the 4 strategic commissioning workstreams, improved market and partner relationships, a shift to prevention and early help, best value and financial stewardship, and improved outcomes for people. | Director Commissioning | 
2.2 Building a Service Development Function | To establish a dedicated Service Development function that brings together practice development, quality assurance, systems and insight to drive consistent, evidence-based improvement across Adult Social Care, strengthening organisational grip on quality, performance and outcomes for people. | Director Service Development | 
2.3 ASC Development Programme: Structures and Workforce | Design and implement a neighbourhood‑based ASC structure and workforce model that aligns capacity, capability and accountability to demand, and supports improved flow, prevention and better outcomes for people. | Director Service Development | 
Workstream 2 Overview: Building Delivery Capability

## Slide 52
Purpose | Scope
Design and deliver a refreshed structure and workforce model that enables a shift to sustainable strategic commissioning within NCC, to deliver the 4 strategic commissioning workstreams, improved market and partner relationships, a shift to prevention and early help, best value and financial stewardship, and improved outcomes for people. | Future functions, teams and roles (organisation design) A supporting programme to build skills and capability Strengthened governance and ways of working Improved relationships with partners, the care market and VCFSE
Current phase – Discovery & Design: Key activities | Key Deliverables & Milestones
Baseline current structures Research on best practice models and comparable commissioning capacity Build on Commissioning Development Review to develop new structure and form Co-design with staff from within the team and the wider directorate Establish refreshed governance Develop underpinning OD programme / commissioning toolkit Engage with partners on proposals for change Case for investment in team | Commissioning Development review: complete Feb 2026 Strategic Commissioning Board established: complete Feb 2026 Underpinning governance fully operational: end of July 2026 Baseline and design new structures: Jul 2026 Case for investment: Jul 2026 Engagement and refinement: Aug 2026 Implementation Planning: Sept 2026 Organisational change process: Oct 2026 onwards
Outcomes | CQC alignment
Increased capacity to deliver strategic commissioning priorities Clear accountability and decision-making Improved best value and financial stewardship Improved relationships with the care market, VCSFE and partners Expanded offer for local people; focus on prevention Improved workforce satisfaction | Commissioning development Market sustainability Carers VCFSE sector Assessments
2.1 Strategic Commissioning Development Programme (2 of 2)
SRO: Director Commissioning
Delivery Lead

## Slide 53
Delivery resources | Key risks and mitigations
ASC Strategic Partner Commissioning & Partnerships leadership team HR Finance Ways of Working Coaches | Capacity constraints / data quality (HR / SMEs / finance)→ Prioritise critical path, use T&Fs, escalate early Cross-workstream misalignment→ Shared principles, governance alignment, integration checkpoints Affordability / financial envelope→ Scenario modelling, align with Finance, phased implementation Stakeholder engagement / consensus risk→ Structured workshops, clear ownership, governance escalation
Key stakeholders | Key Dependencies/ Interdependencies
HR Business Partners: Communications: OD & Culture: Finance Business Partner: The C& P workforce ASC operations colleagues Public Health, Communities, and Analytics & Insights People who draw on care and support VCFSE, Health Partners Care providers | HR and OD capacity and workforce processes Finance assumptions and affordability parameters Alignment with other Operating Model programmes
Future phases | 
Continued OD / skills development programme for Commissioning and Partnerships | 
2.1 Strategic Commissioning Development Programme (2 of 2)
SRO: Director Commissioning
Delivery Lead

## Slide 54
Purpose | Scope
To establish a dedicated Service Development function that brings together practice development, quality assurance, systems and insight to drive consistent, evidence-based improvement across Adult Social Care, strengthening organisational grip on quality, performance and outcomes for people. | Design and deliver a new Service Development Function in ASC Bring together practice development, QA, systems and analytics into a single, coherent model Drive improvement in practice standards, pathways and workforce capability Lead service redesign and continuous improvement aligned to CQC and TOM priorities Use data, feedback and lived experience to inform improvement and measure impact
Current phase – Discovery & Definition: Key activities | Key Deliverables & Milestones
Define the operating model, roles and ways of working for the Service Development function Align with wider workforce, QA, Performance & Analytics and system redesign activity Develop a clear case for investment, including benefits, outcomes and financial impact Identify priority areas of improvement (linked to CQC findings and operational pressures) Establish initial governance, reporting and accountability arrangements Plan phased implementation, including early priorities and quick wins | Costed and defined operating model – July 2026 Investment approval through Star Chamber – July 2026 Initial implementation and mobilisation – Sept to Dec 2026
Outcomes | CQC alignment
More consistent, high-quality and relational practice across ASC Clear, shared understanding of what “good” looks like and how it is measured Stronger organisational grip on quality, performance and outcomes Increased workforce confidence, capability and accountability Evidence-based improvement, with clear links between QA, insight and change Better experience and outcomes for people drawing on care and support Improved CQC assessment and external assurance | EDI & Access
2.2 Building a Service Development Function (1 of 2)
SRO: Director Service Development

## Slide 55
Delivery resources | Key risks and mitigations
Delivery Team: Service Development function (practice development, QA, systems and insight) Support from other functions HR, OD, Finance, Performance & Analytics, Digital / systems, Communications (aligned to defined roles and responsibilities) £: To be confirmed (aligned to costed operating model) | Capacity constraints: HR → early engagement to prioritise critical path Cross-workstream misalignment→ Shared principles, governance alignment, integration checkpoints Affordability / financial envelope→ strong case for change / investment, shift of establishment with function Lack of clarity on remit and duplication risk → Mitigation: Clearly defined scope, alignment with other workstreams and single governance framework
Key stakeholders | Key Dependencies/ Interdependencies
HR Business Partners: Communications: OD & Culture: Finance Business Partner: | HR and OD capacity and workforce design Finance assumptions, affordability and benefits realisation Alignment with workforce and structural changes in Operations and Commissioning Performance & Analytics: metrics, reporting and insight Digital / systems: enabling practice-led workflow and system improvements Practice Improvement and Workforce Development: defining and embedding practice standards and improvement activity
Future phases | 
None | 
2.2 Building a Service Development Function (2 of 2)
SRO: Director Service Development

## Slide 56
Purpose | Scope
Design and implement a neighbourhood‑based ASC structure and workforce model that aligns capacity, capability and accountability to demand, and supports improved flow, prevention and better outcomes for people. | Future functions, teams and roles (organisation design) Locality / neighbourhood delivery model (place-based working) Pathways, flow and accountabilities (handoffs, escalation) Workforce modelling (size, skills, affordability) Critical enablers (digital, estates, commissioning, workforce)
Current phase – Discovery & Definition: Key activities | Key Deliverables & Milestones
Baseline current structures, workforce, flow, estates and enablers Define design principles and success measures Develop and test structure and locality model options Identify constraints, risks and dependencies across the Operating Model Establish governance, decision-making and appraisal approach Develop financial modelling, affordability assumptions and investment requirements for the preferred operating model. | Discovery & Baseline: current state (structures, workforce, estates, pathways, demand) – Jul 2026 Design: future model (functions, roles, locality model, flow, workforce assumptions) – Sep 2026 Implementation Planning: transition plans (HR, estates, phasing, governance) – Dec 26 Mobilisation & Early Implementation: deliver structures, locality model, workforce changes – Apr 27 Benefits Realisation: track outcomes, refine and embed the model (continuous improvement)
Outcomes | CQC alignment
Improved flow and reduced delays across pathways Clear accountability and decision-making Workforce aligned to demand and prevention Consistent, person-centred practice Financially sustainable operating model | ASC Front Door Waiting times
2.3 ASC Development Programme: Structures and Workforce (1 of 2)
SRO: Director Service Development

## Slide 57
Delivery resources | Key risks and mitigations
Delivery Team: Heads of Service: Support from other functions £TBC | Capacity constraints (HR / SMEs / operations)→ Prioritise critical path, use T&Fs, escalate early Weak data (demand / workforce assumptions)→ Iterative modelling, validate with operational insight, align with Performance and Analytics programme Cross-workstream misalignment→ Shared principles, governance alignment, integration checkpoints Affordability / financial envelope→ Scenario modelling, align with Finance, phased implementation Stakeholder engagement / consensus risk→ Structured workshops, clear ownership, governance escalation
Key stakeholders | Key Dependencies/ Interdependencies
HR Business Partners: Communications: OD & Culture: Finance Business Partner: The Adults Social Care workforce People who draw on care and support VCFSE, Health Partners Wider NCC colleagues: Estates, DLTs | Practice Improvement & Workforce Development – defines practice standards, capability requirements and outcomes that the future structure must support. Performance & Analytics – provides demand, workforce, activity and forecasting data to inform organisation design and capacity planning. Operational Services Redesign – alignment between future structures, pathways, accountabilities and neighbourhood working. Strategic Commissioning Programmes – ensures structures support market shaping, prevention and partnership working. HR, OD and Estates – critical enablers for workforce transition, organisational change and locality-based delivery. Finance & Governance – affordability, implementation planning and benefits realisation.
Future phases | 
Implementation Planning (2026–27) – develop transition plans, workforce change approach, estates requirements and implementation roadmap. Implementation (2027) – deliver structural, workforce and locality model changes. Embedding & Continuous Improvement (2027 onwards) – monitor benefits, refine the model and respond to future organisational change. | 
2.3 ASC Development Programme: Structures and Workforce (2 of 2)
SRO: Director Service Development

## Slide 58
Programme | Purpose | SRO | Delivery Lead
3.1 Co-production with people | Embed Co-production throughout Adult Social Care and Commissioning so that the lived experience and voices of people are driving all aspects of our work: decisions, quality, priorities and design | Director Co-production | 
3.2 Equality Diversity and Inclusion | To deliver and embed an approach to EDI that ensure decisions consistently make adult social care fairer, more personalised, and more effective for everyone—by tackling inequality and embedding inclusion in everyday practice. | Corporate Director ASC&H | 
3.3 Leadership, Governance & Financial Stewardship | To deliver, demonstrate and provide assurance on strengthened, stable leadership and governance in Adult Social Care; grip on finance and performance to meet required targets. | Corporate Director ASC&H | 
3.4 Data, performance and analytics | To provide Adult Social Care with a clear, trusted and shared understanding of demand, performance and outcomes - through strong corporate data, analytics and insight - so that leaders, managers and practitioners can make better decisions, strengthen accountability and improve outcomes for people. | Director Service Development | 
3.5 Digital | To increase the uptake and inclusion of digital solutions to improve outcomes and deliver efficiency; improve experience for people, staff and partners; shift towards a digital mind set and approach in designing and delivering services. | Director Commissioning | 
Workstream 3 Overview: Critical Enablers for Success

## Slide 59
Purpose | Scope
Embed Co-production throughout Adult Social Care and Commissioning so that the lived experience and voices of people are driving all aspects of our work: decisions, quality, priorities and design | Building in the Enabling Gloriously Ordinary Lives Strategy for ASC develop the structures, tools, methods, capabilities and resources to support successful Co-production
Current phase: Key activities | Deliverables and Milestones
Develop a case for investment in Co-production resources Develop / describe how Co-production will work and influence the directorate Develop a policy for recognizing and remunerating Co-production Develop a first phase priority plan to move forward Develop and test the approach through the TEC Demonstrator | Business case: July 2026 Roadmap / action plan: Sept 2026 Discovery / mobilization of Co-production in TEC Demonstrator: July to Sept 2026
Outcomes | CQC alignment
People with lived experience of adult social care visibly and materially impacting Adult Social Care activities People with lived experience of adult social care embedded in ASC governance A developing pool of people to participate in Co-production | Co-production EDI & Access Carers VCFSE
3.1 Co-production with People (1 of 2)
SRO: Director Co-production

## Slide 60
Delivery resources | Key risks and mitigations
Delivery Team: Strategic Partner support for early phase work Funding / appointment of dedicated resource Leads from 3 core ASC teams to support and influence development £ - funding to be secured for specialist resource and Co-production budget | Capacity constraints → Agree where to start and build out; phased approach to delivery but clear ambition Cultural resistance → strong leadership and experience of embedding Co-production in SRO; link to CQC improvement and Care Act
Key stakeholders | Key interdependencies
All ASC teams: Commissioning & Partnerships, Service Development, ASC operations Other corporate teams undertaking Co-production: alignment The Adults Social Care workforce People who draw on care and support, carers, families, communities VCFSE, Health Partners | All programmes in the Improvement Plan require Co-production with people
Future phases | 
To be informed by Co-production road map and plan – long term approach to embedding and scaling | 
3.1 Co-production with People (2 of 2)
SRO: Director Co-production

## Slide 61
Purpose | Scope
To deliver and embed an approach to EDI that will make adult social care fairer, more personalised, and more effective for everyone—by tackling inequality and embedding inclusion in everyday practice. | Market and Services: embed EDI throughout commissioning, contracting and brokerage; hold providers to account for diverse and inclusive services and workforce Practice & data: include EDI as a golden thread throughout practice and workforce development; prioritise recording of protected characteristics and use data to actively inform supervision, practice and performance Workforce: become an accredited Race Equality Standard department
EDI Discovery phase 1: Key activities | Deliverables and Milestones
Undertake discovery and research to baseline starting point across: commissioning, practice and workforce. Strengths and areas for development Research best practice models and accredited schemes in the ASC sector and beyond Prioritise early actions identified in CQC assessment in parallel with developing the medium term approach | Immediate priorities action plan linked to CQC: July 2026 EDI discovery and research: Aug / Sept 2026 EDI steering group established: July 2026 Discovery report, recommendations and action plan: end of Sept 2026
Outcomes | CQC alignment
Ensure fair access and outcomes; reduce inequalities and discrimination Deliver truly person-centred care – tailor support to people’s culture, identity, and lived experience (intersectionality) Improve EDI data recording to track quality and outcomes through this lens Create an inclusive workforce – attract, retain, and empower diverse staff to deliver better services Evidence of meeting legal and public duties – comply with the Equality Act and public sector equality duty | EDI & Access
3.2 Equality Diversity and Inclusion (1 of 2)
SRO: TBA

## Slide 62
Delivery resources | Key risks and mitigations
EDI delivery lead EDI leads required from 3 core ASC teams £ medium term potential costs associated with accreditation and possibly specialist training | Capacity constraints / overload → Agree where to start and build out; phased approach to delivery but clear ambition Cultural resistance → strong leadership and experience of EDI leadership in SRO and wider leadership team; link to CQC improvement and Care Act
Key stakeholders | Key interdependencies
All ASC teams: Commissioning & Partnerships, Service Development, ASC operations Other corporate teams including corporate leadership on EDI / Public Sector Equality Duty The Adults Social Care workforce People who draw on care and support, carers, families, communities VCFSE, Health Partners | EDI as a golden thread through all programmes in the Improvement Plan
Future phases | 
Ongoing process of strengthening data, accountability and action on EDI across all areas of ASC | 
3.2 Equality Diversity and Inclusion (1 of 2)
SRO: TBA

## Slide 63
Purpose | Scope
To deliver, demonstrate and provide assurance on strengthened, stable leadership and governance in Adult Social Care; grip on finance and performance to meet required targets. | Permanent ASC Senior Leadership team Increased capability and capacity within wider ASC leaders (Heads of Service and Managers) Established governance framework including performance, transformation and improvement, financial performance
Current phase: Key activities | Deliverables and Milestones
Appointment of permanent leadership team: DAS and Directors Review of leadership capacity (as part of team reorganisations and across the directorate) Design of first line management development programme linked to refreshed structures Review, refresh and communication of departmental governance; linkages into corporate governance; linkages into assurance and oversight regime Co-production embedded into governance with people receiving care and support represented on all key decision-making groups | Appointment of permanent leadership team: DAS and Directors – July to December 2026 Refreshed governance: July 2026 Co-production embedded into governance: Sept to Dec 2026 Management development programme: Q1 2027
Outcomes | CQC alignment
Stable leadership team Improving performance: operational, quality and finance Delivery of ASC TOM progressed Lifting of additional oversight from MHCLG and DHSC | Leadership
3.3 Leadership, Governance and Financial Stewardship (1 of 2)
SRO: Corporate Director ASC&H

## Slide 64
Delivery resources | Key risks and mitigations
Delivery Team Senior Leadership team / DLT Strategic Partner Funding for capacity and OD programmes | Availability of external talent => promote Nottingham as an attractive opportunity with likely increasing opportunities for impact under LGR LGR => continue to communicate with neighbouring councils Financial constraints / ability to invest in talent, capacity and capability => continue to engage and make the case for investment
Key stakeholders | Key interdependencies
Corporate / Political Leadership within NCC Neighbouring councils HR and Finance business partners Wider partners – especially NHS | Effective leadership and governance is an essential underpinning requirement for all other programmes
Future phases | 
Note future transition requirements as a result of LGR | 
3.3 Leadership, Governance and Financial Stewardship (2 of 2)
SRO: Corporate Director ASC&H

## Slide 65
Purpose | Scope | 
To provide Adult Social Care with a clear, trusted and shared understanding of demand, performance and outcomes - through strong corporate data, analytics and insight - so that leaders, managers and practitioners can make better decisions, strengthen accountability and improve outcomes for people. This programme focuses on developing the data, analytics and reporting capability needed across ASC, to ensure data is high quality, well-governed, and actively used to drive improvement, commissioning and strategic planning. | Demand, activity and performance data across ASC Operations, Commissioning & Partnerships, and Service Development Outcomes and impact measurement (including Strategy-aligned outcomes) Data quality, standards and consistency System discovery and optimisation (case management, reporting tools, market analysis) Analytical capability (insight, modelling and forecasting) Data sharing and integration across ASC and partners | 
Current phase – Discovery & Definition : Key activities, Deliverables and Milestones |  | 
Data & insight foundation (May–Jul 2026): Define priority metrics, outcomes framework and reporting requirements aligned to the ASC Strategy and TOM; Identify key data quality issues, gaps and inconsistencies affecting confidence in reporting; Establish the Performance and Quality Board Corporate alignment (Jun–Sept 2026): Establish joint approach with corporate A&I team on roles, responsibilities, delivery model, data governance, standards and ASC ownership Analytical capability & demand insight (Jun–Sept 2026): Developed initial analysis of demand, flow and pressure points across pathways; Identified priority areas for deeper modelling, forecasting and strategic analysis Reporting and architecture approach (Jul–Autumn 2026): Defined future approach to reporting (dashboards, self-service, automated reporting); Set out options for data architecture and integration across systems and partners System insight (supporting activity): BetterGov discovery completed to inform wider data, reporting and workflow improvements (with delivery aligned to other programmes) Mobilisation planning (Autumn 2026): Develop roadmap for delivery of improvements; agreed governance, resourcing (including corporate dependencies) and early priorities |  | 
Outcomes | CQC alignment | CQC alignment
A single, trusted and shared understanding of demand, performance and outcomes across ASC Improved decision-making at all levels, informed by timely, meaningful insight Increased confidence in data quality, consistency and governance Reduced reliance on manual reporting and multiple versions of the truth Stronger ability to analyse demand, predict future pressures and inform strategic planning Data and insight actively used to drive service design, commissioning and workforce planning Clearer performance framework aligned to outcomes and what matters to people Strengthened accountability, assurance and organisational grip |  | Performance EDI & Access
3.4 Data, Performance & Analytics (1 of 2)
SRO: Corporate Director ASC&H

## Slide 66
Delivery resources | Key risks and mitigations
Core delivery team: (Performance & Analytics / A&I / Digital) Input from operational leads across ASC System and digital support (IT / transformation)Programme management and governance support External expertise (if required for system/data architecture) | Data quality and governance – Poor quality, inconsistent data and unclear ownership undermine confidence in reporting and decision-making. Mitigation: Establish clear data ownership, agreed standards and routine data quality assurance. Capacity and dependencies – Limited analytical, digital and corporate resource delays delivery and reduces pace of improvement. Mitigation: Prioritise critical outputs, align resources through governance and escalate constraints early. Funding and delivery constraints – Insufficient funding or delivery capacity limits implementation of reporting, analytics and system improvements. Develop phased delivery options, focus on highest-value improvements and secure investment through robust business cases.
Key stakeholders | Key Interdependencies
Heads of Service and operational teams Digital / IT services Finance, Commissioning & Partnerships and Analysis & Insight Communications and governance leads Partners (NHS, Place Based Partnerships, VCSE where data sharing required) | Operational Redesign – pathway insight, workflow improvement and system optimisation. Practice Improvement & Workforce Development – defines quality standards, outcomes and performance measures. Structures & Workforce – workforce modelling and locality design depend on robust demand and activity data. Commissioning Programmes – requires forecasting, market intelligence and impact reporting. Corporate A&I, Digital & IT – data governance, reporting, analytics and technical delivery. Leadership & Governance – relies on trusted performance, quality and financial insight for assurance and decision-making.
Future phases | 
Foundation & Discovery (2026) – establish governance, data standards, reporting requirements and priority improvements. Mobilisation (Late 2026) – deliver early reporting, dashboard and data quality improvements. Implementation (2027) – embed analytics, forecasting, automated reporting and insight-led decision-making. Embedding & Continuous Improvement (2027–2028) – mature reporting, benefits realisation, data quality and organisational use of insight. | 
3.4 Data, Performance & Analytics (2 of 2)
SRO: Corporate Director ASC&H

## Slide 67
Purpose | Scope
To increase the uptake and inclusion of digital solutions to improve outcomes and deliver efficiency; improve experience for people, staff and partners; shift towards a digital mind set and approach in designing and delivering services. | NCC TEC Demonstrator Exploration of wider digital solutions linked to service redesign Embed digital approaches into commissioning and contracts Strengthen local digital and innovation partnerships
Current phase: Key activities | Deliverables and Milestones
NCC TEC demonstrator mobilisation Mobilisation workshop to define workstreams, timelines, risks, dependencies, key milestones and the critical path End to end citizen journey mapping Develop to Co-production approach for the TEC demonstrator Initial stakeholder identification and engagement | NCC TEC demonstrator mobilization: July to October 2026 NCC TEC demonstrator go-live: November 2026
Outcomes | CQC alignment
Increased use of technology for prevention and to promote independence Use of technology to positively impact demand for care Greater take-up and use of technology as part of care delivery Stronger local digital and innovation partnerships | ASC Front Door
3.5 Digital (1 of 2)
SRO: Director Commissioning

## Slide 68
Delivery resources | Key risks and mitigations
Digital Commissioner Nottingham on call IT Change and transformation £ funding for investment linked to business cases | Change support and adoption Redesign capacity to maximise impact Support and capacity from IT
Key stakeholders | Key interdependencies
People receiving care and support NNCA Local universities Care providers Other partners | WS2: building delivery capability – embedding digital tools into the workforce WS1: Embedding digital approaches to care delivery into how the local market operates and delivers care
Future phases | 
Development of a wider digital roadmap for ASC commissioning, operations, markets and partners Innovation and research – maximising local academic partnerships | 
3.5 Digital (2 of 2)
SRO: Director Commissioning

## Slide 69
6. Delivering the Improvement Programme

## Slide 70
Plans are meaningless without effective delivery arrangements. This section sets out key aspects of how the plan will be delivered including:
Governance, roles and responsibilities
Approach to risk management
Evidencing impact: Logic Model
Corporate support requirements
Communications and stakeholder engagement
Approach to Co-production
Plan status and updates
Delivering the Improvement Programme

## Slide 71
Governance for ASC Improvement Programme
The aim of the governance is to focus improvement programme delivery on building the relationship between ASC practitioners and what matters to people, carers and residents.
The improvement programme governance sits within existing governance structures

## Slide 72
  Owns overall delivery, outcomes and assurance to monthly Improvement Board
  Holds system partners & corporate enablers to account
  Chair of monthly Improvement Plan Programme Board
  Own outcomes, benefits and delivery across programme scope
  Accountable for performance, risks, and alignment to strategy
  Strategic stakeholder management; communication & engagement
  Challenge, support, point of escalation at monthly Improvement Plan Programme Board
  Drive day to day delivery, planning, milestones, risks and interdependencies
  Reporting (assurance, escalation, risks, performance, impact)
  Co-ordination with other Programme Delivery Leads
  Communication and engagement with teams and wider stakeholders
  Delivery / accountability at project and programme level
  Time-limited delivery of defined outputs to time, quality and scope
  Connecting IP projects / activities with BAU
  Escalate risks, blockers and decisions. Communicate with wider teams
  Project / Task & Finish Groups cadence as required
  The voice of the citizen and workforce can be included at any governance point
  Idea and solution generation and decision making
  Provide advice, support and lived-reality checks
  Lived and living experience to influence throughout the programme
Improvement Programme roles and responsibilities
Citizen Subject Matter Experts
Subject Matters Experts
Project Leads
Programme Delivery Leads
Programme Senior Responsible Owner
Improvement Plan Senior Responsible Owner
Roles and grip
Clear accountability from strategy to delivery
A single line of sight from Improvement Plan - programmes - projects - outcomes
Named accountability at every level, aligned to governance and reporting cadence
Delivery ownership sits with individuals, not groups
How performance is managed:
Monthly reporting through programme and board governance
Integrated view of performance, quality and finance
Active management of risks, issues and dependencies
Escalation through defined governance routes

## Slide 73
Clear leadership at all governance levels
  Named delivery owners at project, delivery programme, and strategic programme level
  Chairs to model ways of working, ensure meetings are effective and people leave meetings clear about their actions and how to progress them
  Chairs to meet 6-monthly to discuss what is and isn’t working and ensure any changes in approach are aligned across the governance structure
How the culture shifts:
  Opportunities for the voice of lived and living experience to be heard at all governance levels
  Purpose for every meeting with consistent templates for agendas, reporting, and communicating
  Collective approach to communication with intentional and considered messaging and storytelling agreed at each meeting – what do we want people who aren’t in the room to hear about today
  Coordinated working across the programme with an emphasis on transparency and collaboration
Governance culture and leadership

## Slide 74
Risk | Description | Impact | Original RAG | Mitigation | Adjusted RAG
Capacity and delivery bandwidth | Insufficient people to lead and deliver the very broad programme of work alongside the day job across ASC, commissioning, service development and corporate functions | Improvement plan slips; progress is delayed; programme overload / lack of prioritisation. Medium term financial impact on demand / costs of failing to implement prevention approach and practice improvement | RED | Additional short-term capacity Appointment of ASC Strategic Partner Explicit phased plan Clear prioritisation (phase 1 vs later) Dedicated programme capacity (PMO / delivery leads) Clear critical path Stop/defer low priority work Task & finish model for critical design work Escalation routes via governance | AMBER
Workforce engagement & change fatigue | Capability, practice and capacity – undermining adoption of new practice model and ways of working | Improvement plan relies heavily on relational practice, behaviour change and new structures | RED | Strong communications and engagement approach Visible leadership and sponsorship Co-production with workforce Early wins and demonstrators Celebrating success | AMBER
Financial position | In-year challenge distracts from medium term delivery of improvement and financial sustainability | MTFS savings requirements constrain ability to invest in transformation | RED | Clear link between redesign and financial outcomes Phased investment with ROI (e.g. TEC case) Strong governance and oversight | AMBER
Failure to deliver practice change | Target operating model and strategy not translating into consistent practice on the ground | Critical dependency requiring model being brought to life and tangible | RED | Practice framework + QA Supervision and performance alignment Linking practice to data and outcomes | AMBER
Risks are managed real time and reported monthly through governance. High level risks are set out below:
Managing risk (1 of 2)

## Slide 75
Risk | Description | Impact | Original RAG | Mitigation | Adjusted RAG
System and pathway redesign | Inability to redesign end-to-end pathways (particularly front door, flow, handoffs and transfers of care) Skills, stamina and resilience, capacity | Directly linked to weakest CQC areas: “safe pathways, systems and transitions” | RED | Dedicated pathway redesign programme (Phase 1) Cross-team ownership (ops; commissioning; partners) Data-led design and testing | AMBER
Stakeholders and Partners | Failure to secure shared ownership and alignment with system partners | Many outcomes depend on discharge pathways; neighbourhood model; prevention | RED | Joint governance Integrated pathway design Shared outcome measures | AMBER
Data and analytics | Poor data quality, fragmented systems and limited analytics capability undermine decision-making and performance management | Lack of a single, trusted view | RED | Delivery of Performance & Analytics programme System optimisation (e.g.Liquidlogic) Clear data ownership and standards | AMBER
Market / providers | Provider market fragility limits ability to deliver redesigned pathways and achieve outcomes | Strained provider relationships and market issues | RED | Strengthened commissioning and market shaping Engagement and Co-production Pricing and contract reform | AMBER
LGR and system change | External changes (e.g. LGR, policy changes, ongoing DHSC/CQC scrutiny) disrupt delivery | Could slow progress or require re-design | AMBER | Modular design of TOM Phased implementation Regular review and adaptation | AMBER
Managing risk (2 of 2)

## Slide 76
Workstream activities | Outcomes | Impact
Workstream 1: Improving outcomes for People
1.1 Living Well Earlier
1.2 Living Well at Home
1.3 Living Well with Complexity
1.4 Enabling a System that Works
1.5 Practice Improvement and Workforce Development
Workstream 2: Building Delivery Capability
2.1 Strategic Commissioning Development Programme
2.2 Building a Service Development Function
2.3 ASC Development Programme: Structures and Workforce
Workforce and practice
Practice is consistent across teams and pathway
Staff have clearer roles, ownership, accountability and continuity
Managers and practitioners are more confident
QA and learning are embedded into everyday practice
ASC has a sustainable workforce model aligned to demand, prevention and best value
Staff understand, trust and are part of clear governance & decision-making
Practice is preventative, equity-driven, relational, safe and humane
Translating our commitments into measurable outcomes and impact
People and communities
People experience more consistent, timely, person-centred support
People are supported earlier to stay independent for longer
Access to clear information and advice improves
People have greater choice, control and personalised support
People experience joined-up, easier-to-navigate support
Life led not service led
Care and support is closer to home and neighbourhood based
Preventative by default
Services are coproduced as standard
Financial stewardship
Reduced spend on crisis-led and long-term care
Better value through improved commissioning and redesign
Resources aligned to outcomes and independence
Financial risk proactively managed
People in Nottingham live more independent, healthier lives for longer, with support shaped around what matters to them
More people remain independent without long-term care
Fewer people experience crisis-led interventions
People experience one system, not multiple services
Inequalities in outcomes reduce across neighbourhoods
Adult social care operates as a joined-up, prevention-focused system rather than a reactive service. Life-led not service-led
Demand shifts from crisis & long-term care → early help and community support
Pathways flow more effectively with fewer delays, hand-offs and duplication
Health, housing and social care operate in a more coordinated way
Market capacity better matches local need (including complexity)
Quality, safety and assurance are embedded and demonstrable at all levels
Improved consistency of practice across teams and pathways
Risks are identified and managed earlier and more effectively
CQC assurance is systematic and sustained, not reactive
Learning and improvement are continuous and evidence-led
Decisions are driven by a single, trusted view of demand, performance and outcomes
Single, trusted view of demand and performance
Leaders have real-time visibility of pressure and risk
Decisions are evidence-led
Performance, quality and finance aligned
Financial stewardship: resources are used sustainably, with a better balance between cost and outcomes
Reduced spend on high-cost, crisis-led and long-term care
Better value from commissioned services and in-house provision
Financial risk is proactively managed through data and insight
Investment shifts toward prevention and community-based solutions
Partnerships and system
System operates as one, not fragmented services
Pathways flow with fewer delays and hand-offs
Health, housing and ASC are coordinated
Market capacity aligns with local need
Shared ownership of outcomes across partners
Performance and Accountability – Logic Model
Improvement Plan Logic Model: Performance and Accountability
Workstream 3: Critical Enablers for Success
3.1 Co-production with People
3.2 Equality, Diversity & Inclusion
3.3 Leadership, Governance & Financial Stewardship
3.4 Data, Performance & Analytics
3.5 Digital
Enabling Gloriously Ordinary Lives Strategy

## Slide 77
In order to successfully deliver the plan we will need the expertise and capacity of our colleagues in other parts of the council. Specifically:
HR: establishment baselines, advice and delivery support for organisational change processes, role definition, pay grades and benchmarking
Finance: financial modelling, savings tracking and benefits realisation, support with business cases and investment decisions, and on-going budget monitoring aligned to service demand and activity
Data and analytics: development of a single trusted view of demand, performance and outcomes; data quality improvement; reporting and dashboards; advanced analysis to support decision-making, forecasting and strategic planning; market supply and demand analytics
Commercial (procurement): procurement advice and delivery, including sourcing, tendering and contract award activity, ensuring compliance with governance requirements and timely mobilisation of services
IT: system change and enhancements, implementation of digital tools, front door digital solutions
Communities: insight and engagement with local communities, support for Co-production and development of community-based approaches that strengthen prevention and early support; sharing / alignment of place-based intelligence
Property / Estates: ensuring the workspace, co-location and physical environment support new ways of working, including integrated teams and community-based delivery
Communications: development and delivery of clear internal and external communications, supporting engagement with staff, partners and people who draw on care, and helping to embed change across the organisation
Change Delivery: programme, project management, business analysis and OD & Culture support to design, deliver and embed change
Corporate Support & Resources

## Slide 78
Voluntary, community, faith and social enterprise organisations and groups
Citizens, including people who use ASC services and their carers
Councillors, particularly portfolio holders
Corporate Leadership
Health partners - Integrated Care Board and NHS providers including Primary Care Networks
Wider NCC staff and leaders – especially Public Health, Communities, and Analytics & Insights
ASC staff, including practitioners, operational leads, commissioners and senior leaders
Collaborating effectively to ensure future services are:
  Care act compliant
  Person-centred
  Digitally & data enabled
  Coproduced & coordinated
  Clear & simple by design
  Provide best value
  Continually improving
Regulators
DHSC
CQC
MHCLG
LGR neighbours
Communications and Stakeholder Management
Improvement Board, Independent Chair and Envoy
Communication and stakeholder management is embedded throughout the plan. A separate communications and engagement plan is in development to support delivery. This will address the following key stakeholders:

## Slide 79
Where we are now
We recognise Co-production is not embedded across Adult Social Care and this was reflected in our CQC assessment. Engagement has been inconsistent and often consultative
We have taken early steps, including engagement to shape the ASC Strategy, which is a key foundation for this Improvement Plan.
We are using the TLAP Ladder of Co-production approach to identify where we are in our Co-production maturity
Where we are going
Mainstreaming meaningful Co-production as business as usual
Shared decision-making and co‑design embedded in:
  Strategy
  Service and pathway design
  Commissioning and market shaping
  Evaluation and continuous improvement
Our Co-production Trajectory

## Slide 80
Mainstreaming Co-production as business as usual
We have established a dedicated Co-production programme within the Improvement Plan to drive this shift.
Key elements include:
Programme approach
Co-production embedded as a core enabler across all workstreams, not a standalone activity
Clear expectation that all programmes demonstrate how people have shaped design and decisions
Building capability
Development of a Co-production business case to define sustainable investment, capacity and approach
Strengthening capability across workforce and partners to work in co-productive ways
Structures and governance
Establishing consistent routes for involvement and influence (forums, panels, targeted engagement)
Embedding Co-production into programme governance and decision-making processes
Working with communities and partners
Strengthening relationships with VCSE organisations and community networks to reach diverse groups, amplifying reach and feedback
Creating more neighbourhood-based and accessible opportunities for involvement
How we will Deliver our Co-production Ambitions

## Slide 81
Stronger relationships with communities and partners, including people with lived experience in governance
We will co-produce key elements of the Improvement Programme, including:
  Pathway redesign (front door, assessment, reviews)
  Practice model and what good looks like
  Commissioning intentions and service design
We will ensure people’s lived experience directly influences decisions, not just informs them
People and carers experiencing genuine influence over decisions that affect their lives
We will close the feedback loop, demonstrating clearly how input has shaped outcomes
We will monitor progress through:
  Evidence of Co-production in delivery plans
  Feedback from people and communities
  Improved CQC outcomes, particularly in people’s experience; partnerships and communities and equity & involvement
How we will Deliver our Co-production Ambitions

## Slide 82
This version of the ASC Improvement Plan has been refreshed plan to incorporate CQC feedback and improvement priorities.
Whilst the overall programme structure is unlikely to change, the Improvement Plan needs to be maintained and updated to continue to be a useful and relevant tool to drive improvement.
Moving forward the plan will be reviewed and updated annually in line with business planning and will be presented through governance for approval
In year, any changes to scope and priorities within individual programmes will be agreed within programme delivery groups or at individual project level. SRO’s are responsible for agreeing any changes within their programme areas
Significant changes to scope and priorities will be reported through to the Improvement Plan Programme Board. SROs are responsible for flagging and reporting any significant changes to scope
Risk registers and active risk management will be maintained throughout
Plan Status and Updates

## Slide 83
Appendix 1: Progress to date

## Slide 84
Activity | Date Delivered | Context/Significance
Vision Workshops | Summer 2025 | Established a shared vision and principles for the ASC transformation and Target Operating Model with the workforce and partners.
Engagement with PBP around INTs | Summer 2025 | Early engagement with partners to shape integrated neighbourhood working and multi-agency delivery.
Rollout Magic Notes | November 2025 | Enables more consistent, strengths-based “what matters” conversations with citizens, rather than Practitioners focusing on note-taking.
DLT re-formed | February 2026 | Strengthens senior leadership capacity and oversight to drive improvement and change.
Commissioning Development Review completed | February 2026 | Provided a baseline assessment of commissioning strengths and gaps to inform improvement priorities.
Digital Innovation Business cases drafted | June 2026 | Defined investment priorities to support digital-enabled practice, insight and system improvement.
Reset of strategic relationship with ICB | June 2026 | Re-established joint working foundations with health partners to support integrated delivery.
Strategic engagement with market initiated | February 2026 | Strengthened provider engagement through fee uplift discussions, pricing reform consultation and ongoing collaboration with sector partners (including Notts Care Association and VCSE)
Accommodation Review and Market Analysis commenced | March 2026 | Developed understanding of housing demand and supply to inform future accommodation strategy.
Appendix 1: Progress to date

## Slide 85
Activity | Date Delivered | Context/Significance
What Matters Assessment form Test & Learn initiated | March 2026 | Tested a new assessment approach to embed strengths-based, person-led practice in delivery.
TEC Digital Demonstrator – Diagnostic options appraisal completed | March 2026 | Identified options for scaling technology-enabled care to support independence and prevention.
Brokerage Task & Finish Group to determine options for redesign project | February 2026 | Generated evidence and options to inform the Brokerage redesign and improve commissioning flow.
Strategic Commissioning Board established | February 2026 | Created governance to provide strategic oversight and alignment of commissioning activity.
Commissiong Intentions drafted and finalised | February-April 2026 | Sets clear commissioning priorities aligned to prevention, independence and Best Value.
Creating Best Value Report and Business Case drafted | March 2026 | Established the case and rationale for transformation and system redesign.
Liquid Logic upgrade delivered | April 2026 | Improved core system functionality to support better data quality, workflow and performance insight.
TOM Delivery Group reestablished and remit defined | April 2026 | Strengthened programme governance to coordinate and oversee operating model delivery.
Improvement plan drafted | March 2026 | Brought together programmes and workstreams into a single, coherent transformation plan.
Draft ASC Strategy released | January 2026 | Set the long-term strategic direction co-produced with residents, carers and partners.
BetterGov System Discovery work commenced | May 2026 | To build a clear picture of how Liquidlogic (LAS) is currently used to inform targeted, evidence‑led system improvements.
Appendix 1: Progress to date